## Sheet1
ID | Activity | Description | Reproduction steps | Serverity | Code Author | Found by | Found on | Fixed on | Rechecked on | Fixed | Not Fixed | Not Reproducible
1 | Carousel | Small overlap on the news article title. | News article introduction is too long | L | Stelios Ioannnou | Bradley Read | 27/02/2018 | 27/02/2018 | 27/02/2018
2 | App wide | App crashes on launch. | App is removed from phone task history, phone cache is manually cleared and finally the app is launched with internet/data off. | H | Stelios Ioannnou | Bradley Read | 27/02/2018 | 27/02/2018 | 27/02/2018
3 | Home page | Can not click on images to navigate the app. | On small screen devices when turned landscape the image icons are resized too small meaning that they can not be clicked at all. | H | Stelios Ioannnou | Bradley Read | 27/02/2018 | 27/02/2018 | 27/02/2018
4 | All | When the home button is pressed from within an activity if the application is reloaded it restarts at the main activity. | Open the app, navigate to an activity from the main activity, press the phone's home button and relaunch the application. | M | Stelios Ioannnou | Alex Peebles | 21/03/2018 | 21/03/2018 | 22/03/2018
5 | Home page | Card buttons below the carousel do not always update correctly. | When the user holds their finger between cards the icons below do not always update correclty | L | Stelios Ioannnou | Alex Peebles | 23/03/2018 | 23/03/2018 | 24/03/2018
6 | Home page | Menu does not scale well on tablet. Image attached in file | load application on a 10'' tablet or emulator | L/M | Stelios Ioannnou/Sam Clayton | Alex Peebles | 23/03/2018
7 | Home page | Title of the carousel clips on Moto G | Open home page on small screen phones and hold phone landscape | L | Stelios Ioannnou | Alex Peebles | 23/03/2018 | 23/03/2018 | 23/03/2018
8 | Maps | Title of places category is NewsActivity |  | H | Stelios Ioannnou | Alex Peebles | 23/03/2018 | 23/03/2018 | 23/03/2018
9 | Find Nearest/Places | Scrolling through the Places Activity is really laggy on both the Moto G and my OnePlus 3. I think it's being caused by the maps not displaying until they've loaded as they have to be reloaded after they leave the phone's view. | Visit places activity and select a category. | M | Stelios Ioannou | Alex Peebles | 24/03/2018 | 25/03/2018 | 26/03/2018
10 | Contact/Report | Contact form invalidation messages do not auto display as seen on the Report page (not sure which one is correct). | Click Send Message button on either page when fields are all empty. | L | Olivija Guzelyte/Alex Pullen | Bradley Read | 25/03/2018 | 17/04/2018 | 17/04/2018
11 | Report | Invalidation icons or out of line on the Report page. | Click Send Message button on Report page when fields are all empty. | L | Olivija Guzelyte | Bradley Read | 25/03/2018 | 17/04/2018 | 17/04/2018
12 | Report | Other invalidation icon clips with the other radio button. | Click Send Message button on Report page when subject fields is empty. | L | Olivija Guzelyte | Bradley Read | 25/03/2018 | 17/04/2018 | 17/04/2018
13 | Home page | No internet text on carousel is too low down, | Turn off wifi, clear cache and view the homepage | L | Stelios Ioannou | Alex Peebles | 27/08/2018
14 | Contact/Report | Completion message dissapears too quickly. (Basically just add a Toast popup for complition) | Send a valid message on either the Contact or Report form. | L | Olivija Guzelyte/Alex Pullen | Bradley Read | 29/03/2018 | 17/04/2018 | 17/04/2018
15 | Report | Can send a report with empty other field. | Select Other radio button and leave the specify filed empty. | M | Sam Clayton | Bradley Read | 2018-05-04 | 17/04/2018 | 17/04/2018
16 | Report | Automatically selected the First Name field. | Load the report page. | L | Alex Pullen | Bradley Read | 2018-05-04 | 17/04/2018 | 17/04/2018
17 | Report/Contact | App crashes if you try to submit a form with an email that donesn't exist | Using a valid email address that doesn't exist such as "a@h.com" causes the application to crash. | M | Olivija Guzelyte/Alex Pullen | Alex Peebles | 2018-05-04 |  | 2018-06-04
18 | Report | Report subject warning icon is out of line with the other icons. | Try submitting a report form with no report subject button pressed. | L/M | Sam Clayton | Alex Peebles | 2018-05-04 | 17/04/2018 | 17/04/2018
19 | Report | Opening the keyboard in the message TextArea Pushes the action bar into the notification area when the warning icon is displayed. | Submit a form with an empty message field and select the text area to open keyboard | L | Olivija Guzelyte/Alex Pullen | Alex Peebles | 2018-05-04 | 17/04/2018 | 17/04/2018
20 | Settings | Notifications are received inconsistently to the sliders state. | Change the sliders state and then issue a notification. | M | Stelios Ioannou | Bradley Read | 2018-07-04 | 17/04/2018 | 17/04/2018
21 | Twitter | Favouriting on the app does not properly update if something is unfavourited on twitter and vice versa |  | L/M | Sam Clayton | Alex Peebles | 2018-10-04 |  | 2018-10-04
22 | Offline | Typo in offline text. "cellural", "on,then" | Go offline. | L | Stelios Ioannou | Katrina Tang | 14/04/2018 | 17/04/2018 | 17/04/2018
23 | Report/Contact | Error message still triggers when message is 20 characters | Write a message exactly 20 characters long and click Send Message. | L | Olivija Guzelyte/Alex Pullen | Katrina Tang | 14/04/2018 | 17/04/2018 | 17/04/2018
24 | Contact | Clicking the "Go" button on the map opens and centres Maps on the place last searched for (the Googleplex if never been used before) | Click the "Go" button on the map on the Contact page. | M | Stelios Ioannou | Katrina Tang | 14/04/2018 | 17/04/2018 | 17/04/2018
25 | Contact | Opening google maps loads 30 Astley Road and not 20-22 Astley Road. | Lanch the map in Google Maps. | M | Stelios Ioannou | Bradley Read | 17/04/2018 | 17/04/2018 | 17/04/2018